LIFELONG LEARNING PROGRAMME

GRUNDTVIG

Progress report form 2008 for

Learning Partnerships

(grant agreement period 1.8.2008 – 31.7.2010)

Please send this report to your National Agency, duly completed and signed by 30 June 2009 as requested in Article 7 (Monitoring, Evaluation and Control) of your Grant Agreement. The report will be used by your National Agency for monitoring purposes.

# general information

(From LLPLINK)

| Grant agreement number | 2008-1-FI1-GRU06-00110 1 |
| --- | --- |
| Title of the Partnership | Understanding the Value of Adult Learning |
| Acronym (if applicable) | UVAL |
| Working language of the partnership | English |
| Name of your institution / organisation | Omnia, The Joint Authority of Education in Espoo Region |
| Role of your institution / organisation | x The coordinator  A partner |

| Other participating institutions / organisations (name and country) | The Cyprus Institute of Marketing, Cyprus Haapsalu Vocational Education Centre, Estonia Secondaria I° grado “Rocco Caminiti”, Italy Centrum Kształcenia Ustawicznego Nr 5, Poland Centro de Educación de Personas Adultas del Nalón, Spain The Centre for Employment and Enterprise Development, Bristol, UK |
| --- | --- |

# institution/organisation data

(FROM LLPLINK)

| Full Legal Name | Espoon seudun koulutuskuntayhtymä Omnia |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Omnia, The Joint Authority of Education in Espoo Region |  |  |  |  |  |  |  |  |  |
| Type of Organisation | Adult Education Provider |  |  |  |  |  |  |  |  |  |
| Legal Status |  Private | x Public |  |  |  | Size |  |  | 2000 adult students |  |
| Commercial Orientation |  Profit | x Non profit |  |  |  |  |  |  |  |  |
| Address | Lehtimäentie 1 D BOX 77700 |  |  |  |  |  |  |  |  |  |
| Postcode | 02070 |  | City | Espoo city |  |  | Region |  |  | Uusimaa |
| Country | Finland |  |  |  | Scope |  |  | Regional |  |  |
| Organisation's national ID (if applicable) | FI 0502454-6 |  |  |  |  |  |  |  |  |  |
| Organisation's website (if applicable) | www.omnia.fi |  |  |  | Organisation's e-mail (if applicable) |  |  | omnia@omnia.fi |  |  |

# contact person

(FROM LLPLINK)

| Title | Mr |  | First name |  | Mika |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Family name | Heino |  |  |  |  |  |  |
| Department | Omnia, Adult Education Center |  |  |  |  |  |  |
| Position | lecturer |  |  |  |  |  |  |
| Work Address | Lakelankatu 1 BOX 77702 |  |  |  |  |  |  |
| Postcode | 02070 | City |  | Espoo city |  |  |  |
| Country | Finland |  |  |  |  |  |  |
| Telephone 1 | +358 9 231 96836 |  |  |  |  | Telephone 2 |  |
| Mobile | +358 46 851 5082 |  |  |  |  | Fax | +358 9 231 98599 |
| E-mail address | mika.heino@omnia.fi |  |  |  |  |  |  |

# Partnership content

1. Please describe briefly the Partnership activities undertaken and the results achieved so far:

Partnership activities are: Poland, Kick off meeting (seminar) Cyprus, Raising the awareness (seminar) Spain, Web-pages design (workshop for students) UK, Student exchange on English and communication (workshop for students) Estonia, Increasing the enrolment (seminar) Finland, Web-pages design (workshop for students) The application has been transformed into action successfully; all the partners are participating, the plan of activities is working and there have been mobilities for both the tutors/staff and the students. Results: new network of adult education providers, new shared knowledge, Moodle, web-pages in progress, handbook has been started, prospectus for both national and international purposes. Some of the results promised in the application are already either being tested or in use: accessing the potential students and raising their enrolment in lifelong learning (this has already been done in several participating institutions) and creating the evaluation and feedback systems of studies (a model of feedback system is being tested among the project partners). Communication in between the international activities via Moodle, WebEx, e-mail, phone. Internal evaluation by web based questionnaires has been executed after every activity/mobility.

2. What problems/obstacles have you met in the implementation of the Partnership, if any? How have these problems been they solved?

Partnership problem: One of the partners (UK) has been quite reluctant to participate in the activities. Also getting information from them has been more than difficult. This has been dealt with numerous discussions and guidance from the coordinator. Communication challenges: Several partners are sending non English speaking representatives to international seminars, which causes some problems in translations and communication. This was a bigger issue in the first meeting, but after that not so much. Discussions helped in this matter as well. Coming as a new member into the project after the contact seminar and after the application has been made is quite challenging. Especially if you are meant to be the project coordinator. Timetables, budget: Getting the timetables (in time) from some partners has been hard. Keeping the agreed budget guidelines also turned out to be difficult for one partner. All the above mentioned difficulties have been successfully dealt with discussions and guidance of coordinator.

| 3. Mobility activities |  |
| --- | --- |
| Minimum number of mobilities planned (please tick as appropriate) |  4  8 x 12  Reduced number of mobilities ___ |

| 4. Mobilities carried out between 1.8.2008 and 30.6.2009 (add rows if necessary) |  |  |
| --- | --- | --- |
| Mobility description | Nr of participating staff | Number of participating learners |
| Poland, Kick off meeting | 3 |  |
| Cyprus, Raising the awareness | 2 |  |
| Spain, Web-pages design | 1 | 2 |
| UK, Student exchange on English and comm. | 1 | 3 |
| Estonia, Increasing the enrolment | 3 |  |
| Total number of mobilities: | 10 | 5 |

| 5. Number of mobilities to be carried out by 31.7.2010: | 10 (25 all together) |
| --- | --- |

6. Grantholder's declaration to be signed by the person legally authorised to sign on behalf of your institution/organisation and by the Partnership contact person in your institution/organisation:

| "We, the undersigned, certify that the information contained in this Final Report is correct to the best of our knowledge." |  |
| --- | --- |
| Date: Place: Espoo Name and position of the contact person: Mika Heino Project Coordinator Signature of the contact person: | Date: Place: Espoo Name and position of the Head of institution/organisation: Sampo Suihko Chief Executive Officer Signature of the Head of institution/organisation: Stamp of the institution/organisation (if applicable) |

******

Including representatives of associated partners and – in the case of mobility involving persons with special needs – accompanying persons